## Community Contact Register
Community Contact Register - Website
Project Number: 2190128
Project Name: Locomotive Workshop, South Eveleigh
Enquiry Number | Date | Enquiry or complaint? | Details of enquiry or complaint | Follow Up
1 | 4.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.
2 | 5.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.
3 | 25.10.19 | Enquiry | Heritage tours | A community group wanted to organise a tour of the Locomotive Workshop for 30 people. Mirvac advised that heritage tours would resume late 2020.
4 | 07.01.20 | Enquiry | Purpose of the erection of the Tower Crane in Bay 4 | Clarification of the reason the Tower Crane was being installed, including faciliation of new fitout for commercial and retail tenants, as well as heritage exhibitions.
5 | 17.01.20 | Enquiry | Request for filming permit. | Filming permit issued.
6 | 22.01.20 | Enquiry | Request for tour of the Locomotive Workshop. | Advised that Locomotive Workshop under construction. Yerraingin rooftop sugested as an alternative.
7 | 29.01.20 | Enquiry | Ensure that the poor working conditions of Locomotive Workshop workers is reflected in heritage interpretation. | Confirmed that heritage interpretation would accurately reflect the poor working conditions in the Locomotive Workshops.
8 | 31.01.20 | Complaint | Request to extent the period of noisy works credit. | The asset management team are in conversation with Post Op to resolve this issue.
9 | 3.2.20 | Complaint | Leaking roof in Bay 14. | Mirvac coordinated repairs to rectify the issue.