## Community Contact Register
Community Contact Register
Project Number: 2190128
Project Name: Locomotive Workshop, South Eveleigh
Enquiry Number | Date | Enquiry or complaint? | Details of enquiry or complaint | Follow Up
1 | 4.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.
2 | 5.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.